## EL CAMINO COLLEGE

#### Office of the Vice President - Administrative Services

MINUTES

CITIZENS’ BOND OVERSIGHT COMMITTEE

January 21, 2009

PRESENT:

__x__ Darlene Love	     	     __x__ Frances Mullan   	  	__x__Richard Browning

_____ Richard Montgomery    __x__ Tom Quintana	  	__x__Megan McLean

Also Attending:  Tom Brown, Ann Garten, Jo Ann Higdon, Bruce Hoerning

Open Meeting:  The meeting was called to order at 3 p.m.

Minutes:  The minutes of November 19 were approved with the following correction:

- Page 1 (Project Updates) Second Bullet – last sentence:  change “Caltrans” to “County of Los Angeles.”

Measure “E” Agenda

- December 15, 2008:

  - A. (Category Budgets and Balances) – This is the condensed version of spending for the past month.

  - B (Contract Amendment) –  This is an LPA request for a fee increase due to the proposed increase in the scope of the Math/Business/Allied Health building.   The project will be in the Office of the Department of the State Architect (DSA).  Construction is expected to begin in January of 2010.  A fourth floor has been added to house the Nursing, Radiological Technology and Respiratory Care programs. The math and business sections will be housed in the lower floors.  There is room for expansion of the Nursing program if it is needed.  Funding will come from Measure E money; there is no State funding in this project.

  - C (Revised Change Order – Bomel Industries – Lot H Parking Structure and Athletic Facilities) - The $614,025 change order has been reduced to $314,437.

  - D (Change Order - Bomel Construction – Lot H Parking Structure and Athletic Facilities)  -  Five changes, mostly at ECC’s request.  We should be getting credit for #3 because it is shorter.  #4 is due to the last engineering company.  With these changes, the new contract amount is $19,953, 038.

  - E  (Purchase Orders)

Nursing Program:  Jo Ann Higdon noted that although nurses are in demand now, operating costs to train them are a challenge.  ECC loses money on every nursing student.  However, many local nurses have been through ECC’s nursing program, and there is strong community support for it.  Student nurses go to local hospitals to do their clinical work, but the hospitals don’t actually give ECC any money.  Bruce Hoerning noted that the nursing area in the new building will be set up like a hospital.   He will bring plans for the building to the next meeting.

Parking Structure: Tom Brown: reported that although ECC was required to pay the $614,025 for the Bomel Industries Lot H Parking Structure change order, since it has been reduced to $314,437, ECC should be getting that money back.  It was also noted that 
although the entire parking structure will not be finished, 350 parking spaces on the ground floor will be available for students and staff at the beginning of the spring semester.   The Parking Structure is scheduled to be completed in May of 2009.

Annual Report:  Ann Garten reported that her office is finished with the Annual Report, except for the audit.  She and Bob Gann will review the commentary and have the committee chair review it also.  Agenda items for the next meeting:  choose new members and/or reappoint current members.  Darlene Love has been a member for two terms already; consequently, a new committee chair must be selected also.  The Annual Report usually goes to the Board in March or April.  Committee members are not required to attend that Board meeting but are welcome to do so.

Open Discussion:

- All community colleges are concerned about where the money will be coming from in the future.

- State-funded projects won’t be funded.  Colleges like Cuesta with a $3 million request for reimbursement from the State will have a hard time collecting the money.

- Jo Ann Higdon reported that she and Bob Gann and Fred Sturner were on the phone with the Chancellor’s Office and went over each ECC/Compton project to decide how to proceed.

Agenda for Next Meeting:

- Choose new members and/or reappoint current members

- Select new committee chair

- Review plans for the Math/Business/Allied Health building (Bruce Hoerning)

Adjournment:  The meeting was adjourned at 3:30 p.m.

PURPOSE:  To inform the public concerning bond revenue expenditures and to actively “review and report” on the expenditure of these funds.  (Ed. Code sec. 15278(a)

osite12109