A.	PROJECT BUDGETS

The Facilities Needs Report prepared May 2002, established preliminary budgets for the renovation or replacement of the buildings reported in the categories identified below.  The Needs Report was the basis for determining the amount of bond funding required to complete the facilities upgrade/modernization program.  The preliminary budgets were revised February 17, 2004, when project scopes and timelines were further defined.  Budgets were also revised as of May 16, 2005.  Also included in the needs report was a listing compiled by division of equipment and technology that needed to be replaced or upgraded.

The following table reports expenditures through January 31, 2006.

GENERAL OBLIGATION BOND FUND CATEGORIES AND PROJECTS

|  | REVISED BUDGET | EXPENDED | BALANCE |
| --- | --- | --- | --- |
| Additional Classrooms and Modernization (ACM) |  |  |  |
| Acquisitions (0201) | 5,000,000 | 705,867 | 4,294,133 |
| Architectural Barrier Removal Phase 2 (0202) | 1,529,000 | 18,582 | 1,510,418 |
| Athletic Education and Fitness Complex (0203) | 15,718,000 | 274,322 | 15,443,678 |
| Bookstore/Cafeteria Conversion to Administration (0204) | 6,084,896 | 73,428 | 6,011,468 |
| Business Building Replacement (0205) | 10,926,189 | 139,877 | 10,786,312 |
| Central Plant (0206) | 10,858,000 | 187,740 | 10,670,260 |
| Child Development Center Phase 2 (0207) | 2,525,000 | 30,573 | 2,494,427 |
| Crenshaw Blvd. Frontage Enhancement (0208) | 1,100,000 | 13,418 | 1,086,582 |
| Fire Academy Structure (0209) | 791,375 | 14,880 | 776,495 |
| Fire Program Facility (0210) | 123,000 | 1,656 | 121,344 |
| Humanities Complex Replacement (0212) | 23,120,064 | 1,972,949 | 21,147,116 |
| Learning Resource Center Addition (0213) | 7,100,000 | 121,824 | 6,978,176 |
| Manhattan Beach Blvd. Parking Structure and Entrance (0214) | 216,232 | 812 | 215,420 |
| Remodeling Phase One (0215) - CLOSED |  | 249,133 | (249,133) |
| Remodeling Phase Two (0216) | 157,625 | 34,611 | 123,014 |
| Remodeling Phase Three (0217) | 8,715,875 | 105,101 | 8,610,774 |
| Science Complex Renovation (0219) | 6,721,738 | 6,477,215 | 244,523 |
| Signage and Wayfinding (0224) | 2,600,000 | 53,905 | 2,546,095 |
| Student Services and Activities Replacement (0220) | 31,928,118 | 405,068 | 31,523,050 |
| Temporary Space and Relocation Costs (0221) | 2,000,000 | 708,337 | 1,291,663 |
| Master Planning (0223) |  | 35,000 | (35,000) |
| Reserve for Contingencies (0299) | 37,748,071 |  | 37,748,071 |
| Total Additional Classrooms and Modernization | 174,963,183 | 11,624,298 | 163,338,886 |
| Campus Site Improvements: Accessibility, Safety / Security (CSI) |  |  |  |
| Asphalt Resurfacing - All Lots (0301) | 400,000 | 14,975 | 385,025 |
| Emergency Generators and Distribution (0302) | 2,265,000 | 17,671 | 2,247,329 |
| Emergency Power to Security Lighting (0303) | 175,000 | 1,365 | 173,635 |
| Entrance - Redondo Beach Blvd. to Lot H (0304) | 400,000 | 4,501 | 395,499 |
| Fencing Replacement and Additions (0305) | 375,000 | 2,926 | 372,074 |
| Landscaping and Irrigation System Replacements (0306) | 2,540,000 | 42,403 | 2,497,597 |
| Lighting - Upgrade / Replace All Lots (0308) | 2,440,000 | 19,036 | 2,420,964 |
| Lot F Parking Structure Improvements (0309) | 1,632,000 | 23,669 | 1,608,331 |
| Lot H Parking Structure (0310) | 8,348,666 | 872,601 | 7,476,065 |
| Paving Replacement - All Walks and Driveways (0311) | 2,187,000 | 17,062 | 2,169,938 |
| Pedestrian Walks at Manhattan Beach Blvd. and Lot E (0312) | REVISED BUDGET 81,600 | EXPENDED 637 | BALANCE 80,963 |
| Security Video (0313) | 180,000 | 7,831 | 172,169 |
| Voice / Data / Signal Site Duct Bank (0314) | 1,945,181 | 84,628 | 1,860,553 |
| Reserve for Contingencies (0399) | 1,757,784 | - | 1,757,784 |
| Total Campus Site Improvements: Accessibility, Safety / Security | 24,727,231 | 1,109,304 | 23,617,927 |
| Energy Efficiency Improvements (EEI) |  |  |  |
| Energy Efficiency Improvements Phase Two (0402) | 2,818,000 | 43,000 | 2,775,000 |
| Reserve for Contingencies (0499) | 215,653 |  | 215,653 |
| Total Energy Efficiency Improvements | 3,033,653 | 43,000 | 2,990,653 |
| Health and Safety Improvements (HSI) |  |  |  |
| Administration (0501) | 4,367,732 | 72,324 | 4,295,408 |
| Art & Behavioral Sciences (0502) | 12,247,136 | 204,843 | 12,042,293 |
| Auxiliary Warehouse (0504) | 105,042 | 1,305 | 103,737 |
| Communications (0507) | 8,223,354 | 220,115 | 8,003,239 |
| Construction Technology (0508) | 943,970 | 16,588 | 927,382 |
| Domestic Water System (0509) | 2,488,800 | 68,622 | 2,420,178 |
| Facilities and Receiving (0510) | 1,985,416 | 141,908 | 1,843,508 |
| Fire Alarm (0511) | 780,800 | 9,056 | 771,744 |
| Firelines (0512) | 1,837,503 | 81,798 | 1,755,705 |
| Hazardous Materials Abatement (0513) | 200,000 | 76,703 | 123,297 |
| Library (0515) | 7,876,509 | 421,587 | 7,454,922 |
| Marsee Auditorium (0516) | 6,670,843 | 112,806 | 6,558,037 |
| Math & Computer Sciences (0517) | 10,761,643 | 190,644 | 10,570,999 |
| Music (0518) | 8,896,846 | 227,342 | 8,669,504 |
| Natural Gas System (0519) | 488,000 | 5,698 | 482,302 |
| North Gymnasium (0520) | 3,248,993 | 257,277 | 2,991,716 |
| Physical Education and Men's Shower (0521) | 4,216,871 | 67,618 | 4,149,253 |
| Planetarium (0522) | 559,465 | 12,921 | 546,544 |
| Pool and Health Center (0523) | 8,273,592 | 140,855 | 8,132,737 |
| Primary Electrical Distribution System (0524) | 13,460,000 | 530,769 | 12,929,231 |
| Reimbursements (0525) | 1,456,353 | 1,456,353 | - |
| Security Systems (0526) | 1,313,664 | 30,245 | 1,283,419 |
| Sewer System (0527) | 1,964,200 | 22,629 | 1,941,571 |
| Social Sciences (0528) | 7,415,520 | 152,161 | 7,263,359 |
| Storm Drain System (0530) | 1,083,909 | 12,532 | 1,071,377 |
| Technical Arts (0531) | 5,600,000 | 108,123 | 5,491,877 |
| Shops (0533) | 10,600,000 | 213,338 | 10,386,662 |
| Reserve for Contingencies (0599) | 8,337,328 | - | 8,337,328 |
| Total Health and Safety Improvements | 135,403,489 | 4,856,160 | 130,547,329 |
| Information Technology and Equipment (ITE) |  |  |  |
| Behavioral and Social Sciences (0601) | 579,077 | 22,984 | 556,093 |
| Business (0602) | 1,123,650 | 438,401 | 685,249 |
| Facilities Planning and Services (0603) | 1,818,724 | 283,304 | 1,535,420 |
| Fine Arts (0604) | 2,805,096 | 328,212 | 2,476,884 |
| Health Sciences and Athletics (0605) | 1,203,993 | 177,688 | 1,026,305 |
| Humanities (0606) | 607,033 | 150,534 | 456,499 |
| Industry and Technology (0607) | 1,771,641 | 422,712 | 1,348,929 |
| Information Technology (0608) | 14,557,510 | 1,784,540 | 12,772,970 |
| Learning Resources (0609) | 4,665,775 | 260,085 | 4,405,690 |
|  | REVISED BUDGET | EXPENDED | BALANCE |
| Natural Sciences (0611) | 3,002,285 | 585,119 | 2,417,166 |
| Nursing (0612) | 252,651 | 116,478 | 136,173 |
| Student and Community Advancement (0613) | 567,500 | 169,879 | 397,621 |
| Interfund Transfer (0614) | 141,150 | 141,150 | - |
| Phase II, III, IV Purchases (0697) | 12,686,900 |  | 12,686,900 |
| Installation Contingency (0698) | 4,464,194 |  | 4,464,194 |
| Reserve for Contingencies (0699) | 3,746,018 | - | 3,746,018 |
| Total Information Technology and Equipment | 54,681,858 | 5,016,082 | 49,665,776 |
| Physical Education Facilities Improvements (PEFI) |  |  |  |
| Baseball Field (0701) | 1,091,800 | - | 1,091,800 |
| North Field (0702) | 481,600 | - | 481,600 |
| Sand Volleyball (0703) | 12,300 | - | 12,300 |
| Reserve for Contingencies (0799) | 121,349 | - | 121,349 |
| Total Physical Education Facilities | 1,707,049 | - | 1,707,049 |
| Refunding Income | 6,866,776 |  | 6,866,776 |
|  | $ 401,383,239 | $ 22,648,843 | $ 378,734,396 |

B.	2004–2005   MEASURE E AUDIT REPORT

It is recommended that the Board accept the revised annual financial and performance audit report prepared by Vicenti Lloyd & Stutzman LLP, for the El Camino Community College Proposition 39 General Obligation Bonds Measure E.  Copies of the audit reports for the 2004–2005 fiscal year have been distributed to the Board of Trustees.  The public may review the audit report in the Office of the Vice President-Administrative Services, Room AD 106.

C.	CITIZENS’ BOND OVERSIGHT COMMITTEE

The next meeting of the Citizens’ Bond Oversight Committee is scheduled for March 1 at 3 p.m.         in the Administration Building, Room 127.

D.	PUBLIC WORKS PROJECT HUMANITIES – CHANGE ORDERS

It is recommended that the contracts of the prime trade contractors listed below be changed by the amounts indicated due to the requested change orders.

Contractor			Amount

HPS Mechanical		CREDIT  ($14,402)

THIS CHANGE ORDER INDICATES CREDITS TO THE DISTRICT

1.	Deduction due to alternate routing and point of connection for new water lines 											($5,621)

2.	Deduction due to alternate routing and point of connection for new natural gas lines 										($8,781)

E.	PURCHASE ORDERS

The following purchase orders have been issued in accordance with the District’s purchasing policy and authorization of the Board of Trustees.  It is recommended that the following purchase orders for Measure “E” expenditures be ratified and that payment be authorized upon delivery and acceptance of the items or services ordered.

P.O.

Number	Vendor Name	Site Name	Description	    P.O. Cost

P0089061      Ctl Environmental Services     Humanities Complex      Site Improvements	     $1,310.00

P0089064	C & A Floor Coverings, Inc.	Remodeling-Phase 2	Buildings	$2,324.01

*P0089065	Dell Marketing L. P.	Faculty Computers	Non Inst Comp Eq 	$304,961.25

Total : 	3	$308,595.26

B0087949	Minco Construction	Fire Alarm	Buildings	$587,000.00

B0089034	Innovative Interface	Instructional Service	New Equipment - Noninstruc	$56,000.00

B0089050	Southern California	Primary Elect Distri	Contract Services	$373,956.75

B0089063	Toft Wolff Farrow	Library	Architecture & Engineering	$5,120.00

Total : 	4	$1,022,076.75

Total POs and BPOs : 	7	TOTAL :	$1,330,672.01

* Originally encumbered from bond funds but will be expended out of current operating budget (Fund 11).