A.	PROJECT BUDGETS

The Facilities Needs Report prepared May 2002, established preliminary budgets for the renovation or replacement of the buildings reported in the categories identified below.  The Needs Report was the basis for determining the amount of bond funding required to complete the facilities upgrade/modernization program.  The preliminary budgets were revised February 17, 2004, when project scopes and timelines were further defined.  Budgets were also revised as of May 16, 2005.  Also included in the needs report was a listing compiled by division of equipment and technology that needed to be replaced or upgraded.

The following table reports expenditures through March 31, 2006.

| GENERAL OBLIGATION BOND FUND CATEGORIES AND PROJECTS Expenditures though March 31, 2006 |  |  |  |
| --- | --- | --- | --- |
|  | REVISED BUDGET | EXPENDED | BALANCE |
| Additional Classrooms and Modernization (ACM) |  |  |  |
| Acquisitions (0201) | 5,000,000 | 705,867 | 4,294,133 |
| Architectural Barrier Removal Phase 2 (0202) | 1,529,000 | 18,582 | 1,510,418 |
| Athletic Education and Fitness Complex (0203) | 15,718,000 | 274,322 | 15,443,678 |
| Bookstore/Cafeteria Conversion to Administration (0204) | 6,084,896 | 73,428 | 6,011,468 |
| Business Building Replacement (0205) | 10,926,189 | 139,877 | 10,786,312 |
| Central Plant (0206) | 10,858,000 | 187,740 | 10,670,260 |
| Child Development Center Phase 2 (0207) | 2,525,000 | 30,573 | 2,494,427 |
| Crenshaw Blvd. Frontage Enhancement (0208) | 1,100,000 | 13,418 | 1,086,582 |
| Fire Academy Structure (0209) | 791,375 | 14,880 | 776,495 |
| Fire Program Facility (0210) | 123,000 | 1,656 | 121,344 |
| Humanities Complex Replacement (0212) | 23,120,064 | 2,819,393 | 20,300,671 |
| Learning Resource Center Addition (0213) | 7,100,000 | 121,824 | 6,978,176 |
| Manhattan Beach Blvd. Parking Structure and Entrance (0214) | 216,232 | 812 | 215,420 |
| Remodeling Phase Two (0216) | 157,625 | 38,337 | 119,288 |
| Remodeling Phase Three (0217) | 8,715,875 | 105,101 | 8,610,774 |
| Science Complex Renovation (0219) | 6,721,738 | 6,477,215 | 244,523 |
| Signage and Wayfinding (0224) | 2,600,000 | 53,905 | 2,546,095 |
| Student Services and Activities Replacement (0220) | 31,928,118 | 440,268 | 31,487,850 |
| Temporary Space and Relocation Costs (0221) | 2,000,000 | 745,767 | 1,254,233 |
| Master Planning (0223) |  | 300,542 | (300,542) |
| Reserve for Contingencies (0299) | 37,748,071 |  | 37,748,071 |
| Total Additional Classrooms and Modernization | 174,963,183 | 12,812,641 | 162,150,542 |
|  | REVISED BUDGET | EXPENDED | BALANCE |
| Campus Site Improvements: Accessibility, Safety / Security (CSI) |  |  |  |
| Asphalt Resurfacing - All Lots (0301) | 400,000 | 14,975 | 385,025 |
| Emergency Generators and Distribution (0302) | 2,265,000 | 17,671 | 2,247,329 |
| Emergency Power to Security Lighting (0303) | 175,000 | 1,365 | 173,635 |
| Entrance - Redondo Beach Blvd. to Lot H (0304) | 400,000 | 4,501 | 395,499 |
| Fencing Replacement and Additions (0305) | 375,000 | 2,926 | 372,074 |
| Landscaping and Irrigation System Replacements (0306) | 2,540,000 | 42,403 | 2,497,597 |
| Lighting - Upgrade / Replace All Lots (0308) | 2,440,000 | 19,036 | 2,420,964 |
| Lot F Parking Structure Improvements (0309) | 1,632,000 | 32,732 | 1,599,268 |
| Lot H Parking Structure (0310) | 8,348,666 | 872,601 | 7,476,065 |
| Paving Replacement - All Walks and Driveways (0311) | 2,187,000 | 17,062 | 2,169,938 |
| Pedestrian Walks at Manhattan Beach Blvd. and Lot E (0312) | 81,600 | 637 | 80,963 |
| Security Video (0313) | 180,000 | 7,831 | 172,169 |
| Voice / Data / Signal Site Duct Bank (0314) | 1,945,181 | 84,628 | 1,860,553 |
| Reserve for Contingencies (0399) | 1,757,784 | - | 1,757,784 |
| Total Campus Site Improvements: Accessibility, Safety / Security | 24,727,231 | 1,118,367 | 23,608,864 |
| Energy Efficiency Improvements (EEI) |  |  |  |
| Energy Effciency Improvements Ph. 1 (0401) CLOSED |  | - |  |
| Energy Efficiency Improvements Phase Two (0402) | 2,818,000 | 43,000 | 2,775,000 |
| Reserve for Contingencies (0499) | 215,653 |  | 215,653 |
| Total Energy Efficiency Improvements | 3,033,653 | 43,000 | 2,990,653 |
| Health and Safety Improvements (HSI) |  |  |  |
| Administration (0501) | 4,367,732 | 80,867 | 4,286,865 |
| Art & Behavioral Sciences (0502) | 12,247,136 | 281,343 | 11,965,793 |
| Auxiliary Warehouse (0504) | 105,042 | 1,305 | 103,737 |
| Communications (0507) | 8,223,354 | 220,115 | 8,003,239 |
| Construction Technology (0508) | 943,970 | 16,588 | 927,382 |
| Domestic Water System (0509) | 2,488,800 | 68,622 | 2,420,178 |
| Facilities and Receiving (0510) | 1,985,416 | 141,908 | 1,843,508 |
| Fire Alarm (0511) | 780,800 | 22,609 | 758,191 |
| Firelines (0512) | 1,837,503 | 85,268 | 1,752,235 |
| Hazardous Materials Abatement (0513) | 200,000 | 76,807 | 123,193 |
| Library (0515) | 7,876,509 | 421,587 | 7,454,922 |
| Marsee Auditorium (0516) | 6,670,843 | 112,806 | 6,558,037 |
| Math & Computer Sciences (0517) | 10,761,643 | 190,644 | 10,570,999 |
| Music (0518) | 8,896,846 | 227,342 | 8,669,504 |
| Natural Gas System (0519) | 488,000 | 5,698 | 482,302 |
| North Gymnasium (0520) | 3,248,993 | 257,277 | 2,991,716 |
| Physical Education and Men's Shower (0521) | REVISED BUDGET 4,216,871 | EXPENDED 67,618 | BALANCE 4,149,253 |
| Planetarium (0522) | 559,465 | 12,921 | 546,544 |
| Pool and Health Center (0523) | 8,273,592 | 140,855 | 8,132,737 |
| Primary Electrical Distribution System (0524) | 13,460,000 | 1,147,992 | 12,312,008 |
| Reimbursements (0525) | 1,456,353 | 1,456,353 | - |
| Security Systems (0526) | 1,313,664 | 30,245 | 1,283,419 |
| Sewer System (0527) | 1,964,200 | 22,629 | 1,941,571 |
| Social Sciences (0528) | 7,415,520 | 152,161 | 7,263,359 |
| Storm Drain System (0530) | 1,083,909 | 12,532 | 1,071,377 |
| Technical Arts (0531) | 5,600,000 | 303,984 | 5,296,016 |
| Shops (0533) | 10,600,000 | 213,338 | 10,386,662 |
| Reserve for Contingencies (0599) | 8,337,328 | - | 8,337,328 |
| Total Health and Safety Improvements | 135,403,489 | 5,771,414 | 129,632,075 |
| Information Technology and Equipment (ITE) |  |  |  |
| Behavioral and Social Sciences (0601) | 579,077 | 22,984 | 556,093 |
| Business (0602) | 1,123,650 | 438,401 | 685,249 |
| Facilities Planning and Services (0603) | 1,818,724 | 283,304 | 1,535,420 |
| Fine Arts (0604) | 2,805,096 | 328,212 | 2,476,884 |
| Health Sciences and Athletics (0605) | 1,203,993 | 177,688 | 1,026,305 |
| Humanities (0606) | 607,033 | 150,534 | 456,499 |
| Industry and Technology (0607) | 1,771,641 | 422,712 | 1,348,929 |
| Information Technology (0608) | 14,557,510 | 1,784,540 | 12,772,970 |
| Learning Resources (0609) | 4,665,775 | 260,085 | 4,405,690 |
| Math (0610) | 688,661 | 134,997 | 553,664 |
| Natural Sciences (0611) | 3,002,285 | 585,119 | 2,417,166 |
| Nursing (0612) | 252,651 | 116,478 | 136,173 |
| Student and Community Advancement (0613) | 567,500 | 169,879 | 397,621 |
| Interfund Transfer (0614) | 141,150 | 141,150 | - |
| Phase II, III, IV Purchases (0697) | 12,686,900 |  | 12,686,900 |
| Installation Contingency (0698) | 4,464,194 |  | 4,464,194 |
| Reserve for Contingencies (0699) | 3,746,018 | - | 3,746,018 |
| Total Information Technology and Equipment | 54,681,858 | 5,016,082 | 49,665,776 |
| Physical Education Facilities Improvements (PEFI) |  |  |  |
| Baseball Field (0701) | 1,091,800 | - | 1,091,800 |
| North Field (0702) | 481,600 | - | 481,600 |
| Sand Volleyball (0703) | 12,300 | - | 12,300 |
| Reserve for Contingencies (0799) | 121,349 | - | 121,349 |
| Total Physical Education Facilities | 1,707,049 | - | 1,707,049 |
| Refunding Income | 6,866,776 | - | 6,866,776 |
| *The Master Planning expenses identified will be spread at a later date. | $ 401,383,239 | $ 24,761,504 | $ 369,754,959 |

### B.	CONTRACTS $50,000 OR HIGHER

It is recommended that the Board of Trustees, in accordance with Board Policy 6340, approve the District entering into the following agreements.  The Vice President – Administrative Services, or his authorized designee has executed the necessary documents.

# 1.	BID 2005-09 HUMANITIES CONSTRUCTION PROJECT

It is recommended that the following prime contractors be awarded contracts for the respective trades related to the construction of the Humanities Building, in accordance with specifications, terms and conditions of the above-named bid. Construction will begin in May 2006 and conclude in the summer of 2007.  C. W. Driver, previously approved by the Board, will manage the construction.

El Camino Community College

Humanities Complex Replacement Project

| Bid Package | Bid Package Description | Low Bidder |  | Bid Award Amount |
| --- | --- | --- | --- | --- |
| 1-1 | Final Clean up | M N Z Janitorial Services |  | $52,570.00 |
| 2-2 | Landscape | Bennett Landscape |  | 262,713.86 |
| 3-1 | Site Concrete | Amtek Construction |  | 1,042,000.00 |
| 3-2 | Structural Concrete | TB Penick |  |  |
|  |  | Base Bid | $6,455,000.00 |  |
|  |  | Alternate 2 | 430,000.00 | 6,885,000.00 |
| 4-1 | Masonry | So Counties Quality Masonry |  |  |
|  |  | Base Bid | 501,000.00 |  |
|  |  | *Alternate 2 | 21,000.00 | 522,000.00 |
| 6-1 | Finish Carpentry | K & Z Cabinet Co. Inc. |  | 135,723.00 |
| 8-1 | Glass & Glazing | Padua Glass Enterprises, Inc. |  | 1,207,400.00 |
| 9-1 | Metal Framing | Superior Wall Systems, Inc. |  | 1,484,330.00 |
| 9-2 | Ceramic Tile | Premier Tile & Marble |  | 168,420.00 |
| 9-3 | Acoustical Ceiling | Preferred Ceilings Inc |  | 728,900.00 |
| 9-4 | Flooring | Pacific Carpets, Inc. |  | 400,000.00 |
| 9-5 | Painting | Borbon, Inc. |  | 249,900.00 |
| 10-1 | Misc. Specialties | Inland Building Companies |  | 235,000.00 |
| 10-2 | Toilet Partitions | Stumbaugh & Associates, Inc. |  | 45,235.00 |
| 14-1 | Elevators | Braaksma Construction |  | 313,000.00 |
| 15-1 | Fire Sprinklers | Orange Builders |  |  |
|  |  | Base Bid | 366,212.00 |  |
|  |  | Alternate 2 | 2,000.00 | 368,212.00 |
| 15-2 | Plumbing | PPC Air Conditioning, Inc. |  | 513,000.00 |
| 15-3 | HVAC | Airemasters Air Conditioning |  | 1,625,000.00 |
| 16-1 | Electrical | S.H. Fish Electric |  | 2,399,900.00 |
|  |  |  | TOTAL | $18,638,303.86 |
| *Alternate 2 - This alternate is the cost associated with shortening the construction schedule by 30 days from August 31 to July 31, 2007 |  |  |  |  |
| In November 2005, the project construction manager estimated the total project cost to be slightly over $31,000,000 for the building and associated work. The results of this round of bidding are within the estimated amount for the work. A revised project budget for this phase of work will be prepared and presented when the costs of the final two bid packages (5-1 Structural Steel and 7-1 Roofing) are determined. Additional Bidding - Two bid packages, 5-1 Structural Steel and 7-1 Roofing, are not being awarded at this time. There were no bidders on the Structural Steel package. Two bids were received for the Roofing package but the amounts are judged to be excessive for the scope of work. Both bid packages are being bid again. Bid Responses – Sixty (60) Bids were received. Five (5) bid packages received only one bid. One hundred and two (102) contractors attended the mandatory pre-construction meetings and job walks. The total amount of bids submitted by the second low bidders and the bid packages that received only one bidder is $20,799,860—i.e., low bid savings of $2,161,557. Budget Background – The Humanities Complex Replacement project budget of $23,120,064 was developed in January 2004 using then current construction cost information. The budget of $22,184,735 is for the building and associated work. The remaining $1,595,329 is the budget amount for the future demolition of the remaining west portion of the Humanities complex and landscaping of that area. The recommended bids for this project indicate that the budget will be inadequate to support the full construction cost and will need to be increased. There are two reasons for the increase: an escalation of construction costs; and an expansion of the project's scope. The scope of this project increased because of an increase in the width of the building corridors beyond the building code minimum. The building code minimum was judged to be too narrow for comfortable circulation. An additional elevator was also added to provide enhanced accessibility. A formal master plan revision will be presented for review and approval to the Board of Trustees after the final Humanities and Parking Structure bids have been approved. |  |  |  |  |

#### 2.	STATEWIDE EDUCATIONAL WRAP-UP (INSURANCE) PROGRAM (SEWUP)

Contractor				Dates of Service		Contract Amount

#### Keenan and Associates		4/15/06-10/15/07		        $644,122

The contractor will provide the District’s Owner Controlled Insurance Program (OCIP) for the Humanities Construction Project under its SEWUP by providing and administering the primary insurance for the project.  All premiums and coverages (General Liability, Workers’ Compensation, Pollution Liability, etc.) are paid by the District.

3.	AMENDMENT

Contractor				Dates of Service		Contract Amount

SC Advisory Services		11/14/05-12/31/06		18% of utility rebate

The contractor is to provide services to obtain utility rebates in accordance with the California Community College & Investor Owned Utilities rebate program.

This is a request to increase the “not to exceed” amount of an existing contract from $49,000 to $180,000.  The prior contract, executed in November 2005, envisioned the potential collection of $250,000 in rebates, which would yield the contractor $45,000.  It has now been determined the potential rebate amount has increased to $1,000,000, which would yield the contractor $180,000.  Previously approved December 19, 2005.

Specific services provided by the contractor include; preparation of rebate applications, calculation and documentation of current and future equipment energy consumption, interface with utility company on District’s behalf and provide follow up with utility representatives when energy conservation measures are completed.

C.	CITIZENS’ BOND OVERSIGHT COMMITTEE

The next meeting of the Citizens’ Bond Oversight Committee is scheduled for April 19 at 3 p.m.         in the Administration Building, Room 127.

D.	PURCHASE ORDERS

The following purchase orders have been issued in accordance with the District’s purchasing policy and authorization of the Board of Trustees.  It is recommended that the following purchase orders for Measure “E” expenditures be ratified and that payment be authorized upon delivery and acceptance of the items or services ordered.

P.O.

Number	Vendor Name	Site Name	Description	P.O. Cost

P0082008	Cummings & Associates	Remodeling-Phase 2	Group II Equipment	$323.15

P0089087	Division of the State Architect 	TemporarySpace/Reloc	Architecture & Engineering	$7,831.97

P0089089	Daily Breeze, the	Master Planning	Advertising-Bond Projects	$4,000.00

Total : 	3	$12,155.12

B0089072	Flewelling & Moody	TemporarySpace/Reloc	Architecture & Engineering	$20,000.00

B0089073	Flewelling & Moody	Primary Elect Distri	Architecture & Engineering	$9,000.00

B0089084	C.W. Driver	Humanities Complex 	Professional Services-Bon	$2,000.00

B0089085	J.T. Thorpe & Son	Fire Academy Structu	Buildings	$12,760.00

B0089088	Allard Engineering	Central Plant	Architecture & Engineering	$48,825.00

Total : 	5	$92,585.00

Total POs and BPOs : 	8	TOTAL :	$104,740.12