Agenda for the El Camino Community College District Board of Trustees

For

Measure E Bond Fund

Administrative Services

Page No.

A.	Citizens’ Bond Oversight Committee Calendar					1

B.	Category Budgets and Balances							1

C.	Contract – Sandy Pringle Associates		 					1

D.	Humanities Budget									2

E.	Modular Building 2006								2

F.	Bond Resolution									2

G.	Purchase Orders and Blanket Purchase Orders 					3

A.	CITIZENS’ BOND OVERSIGHT COMMITTEE MEETING CALENDAR 2006-2007

Meetings will be held in the Boardroom at 3:00 PM on the following dates.

September 27, 2006

November 15, 2006

January 24, 2007

March 14, 2007

May 23, 2007

B.	CATEGORY BUDGETS AND BALANCES

The following table reports Measure E expenditures and commitments through July, 2006.

| CATEGORY | BUDGET | EXPENDED | COMMITTED | BALANCE |
| --- | --- | --- | --- | --- |
| Additional Classrooms and Modernization (ACM) | 175,871,183 | 15,239,219 | 27,347,119 | 133,284,845 |
| Campus Site Improvements (CSI) | 24,467,231 | 1,297,025 | 218,519 | 22,951,687 |
| Energy Efficiency Improvements (EEI) | 3,033,653 | 67,048 | 1,539,000 | 1,427,605 |
| Health and Safety Improvements (HSI) | 134,755,489 | 7,892,251 | 2,163,356 | 124,699,882 |
| Information Technology and Equipment (ITE) | 55,567,921 | 5,079,547 | 67,625 | 50,420,749 |
| Physical Education Facilities Improvements (PEFI) | 1,707,049 | 0.00 | 0.00 | 1,707,049 |
| Refunding Income | 5,980,713 | 0.00 | 0.00 | 5,980,713 |
| TOTAL | 401,383,239 | 29,575,090 | 31,335,618 | 334,491,818 |

### C.	CONTRACT – SANDY PRINGLE ASSOCIATES, INSPECTION CONSULTANTS, INC. (SPAIC)

It is recommended the Board of Trustee’s approve entering into a contract with SPAIC to provide Division of the State Architect (DSA) certified inspectors for various construction projects, including the Lot H Parking Structure and Central Plant projects.

Four inspection firms were interviewed by District and construction program management staff and were evaluated based upon previous experience, staff qualifications, responses to questions and the proposed fee structure.  Due to the large volume of inspection services the District’s construction program requires, two firms were selected, LCC3 and SPAIC.  Since LCC3 is currently under contract and performing services for the Humanities Building Project and Modular Building Project, SPAIC will perform inspection services on the projects referenced above.

Dates of Service:  August 18, 2006 though December 31, 2008.

Cost:  Not to exceed $365,000 invoiced monthly.  The cost is based upon the contractor providing two DSA certified Class 1 inspectors and a projected 13 month schedule for each project.

D.	HUMANITIES BUDGET DETAIL

| CATEGORY | BUDGET | EXPENDED | COMMITTED | BALANCE |
| --- | --- | --- | --- | --- |
| Design & Plan Review | $ 1,701,941.00 | $ 1,183,280.02 | $ 37,331.99 | $ 481,328.99 |
| Construction | 23,562,000.00 | 2,904,163.07 | 19,601,303.36 | 1,056,533.57 |
| Construction Administration | 884,203.00 | 23,515.64 | 628,151.01 | 232,536.35 |
| Testing & Inspection | 1,050,000.00 | 85,021.34 | 300.00 | 964,678.66 |
| Group I & II Equipment | 1,066,100.00 | 0.00 | 0.00 | 1,066,100.00 |
| Contingency | 1,100,000.00 | 0.00 | 0.00 | 1,100,000.00 |
| TOTAL | $ 29,364,244.00 | $ 4,195,980.07 | $ 20,267,086.36 | $ 4,901,177.57 |

E.	MODULAR BUILDING 2006 PROJECT BUDGET

| CATEGORY | BUDGET | EXPENDED | COMMITTED | BALANCE |
| --- | --- | --- | --- | --- |
| Design & Plan Review | $ 159,700.00 | $ 58,741.45 | $ 9,211.32 | $ 91,747.23 |
| Construction | 2,180,000.00 | 803,738.70 | 1,800.00 | 1,374,461.30 |
| Construction Administration | 50,000.00 | 9,341.54 | 0.00 | 40,658.46 |
| Testing & Inspection | 110,000.00 | 0.00 | 3,500.00 | 106,500.00 |
| Group I & II Equipment | 20,000.00 | 0.00 | 0.00 | 20,000.00 |
| Contingency | 154,000.00 | 0.00 | 0.00 | 154,000.00 |
| Moving Expenses | 40,000.00 | 0.00 | 0.00 | 40,000.00 |
| TOTAL | $ 2,713,700.00 | $ 871,821.69 | $ 14,511.32 | $ 1,827,366.99 |

F.	BOND RESOLUTION

It is recommended that the Board of Trustees adopt the Resolution authorizing the issuance and sale of general obligation bonds of the El Camino College District in a aggregate principal amount of not to exceed $150,000,000.

RESOLUTION OF THE BOARD OF SUPERVISORS OF LOS ANGELES COUNTY, CALIFORNIA AUTHORIZING THE ISSUANCE AND SALE OF EL CAMINO COMMUNITY COLLEGE DISTRICT GENERAL OBLIGATION BONDS, ELECTION OF 2002, SERIES 2006B, IN AN AGGREGATE PRINCPAL AMOUNT OF NOT TO EXCEED $150,000,000.

(complete document available in the office of the Vice President of Administrative Services)

G.	PURCHASE ORDERS (PO) AND BLANKET PURCHASE ORDERS (BPO)

The following purchase orders have been issued in accordance with the District’s purchasing policy and authorization of the Board of Trustees.  It is recommended that the following purchase orders for Measure “E” expenditures be ratified and that payment be authorized upon delivery and acceptance of the items or services ordered.

| P.O. NUMBER | VENDOR | SITE NAME | DESCRIPTION | COST |
| --- | --- | --- | --- | --- |
| P0083185 | Best Roofing | Technical Arts | Site Improvements | $20,998.80 |
| P0099000 | CCS Presentation Systems, Inc. | Behavioral/Social Science | New Equipment - Instructional | $54,726.66 |
| P0099002 | Perkin Elmer Corporation | Natural Sciences | New Equipment - Instructional | $23,656.70 |
| P0099003 | CCS Presentation Systems, Inc. | TemporarySpace/Relocation | Group II Equipment | $1,733.80 |
| P0099004 | Boise Cascade | TemporarySpace/Relocation | Group II Equipment | $1,353.13 |
| P0099006 | MTGL, Inc. | TemporarySpace/Relocation | Buildings | $1,800.00 |
| P0099008 | Allard Engineering | Humanities Complex | Architecture & Engineering | $2,500.00 |
| P0099009 | All American Inspection | TemporarySpace/Relocation | Testing & Inspection | $3,500.00 |
| P0099010 | Empire Cleaning Supply | Facilities Planning | New Equipment - Noninstructional | $4,926.07 |
| P0099011 | Southern California Material | Facilities Planning | New Equipment | $3,086.88 |
| P0099012 | C & A Floor Coverings, Inc. | Central Plant | Buildings | $5,300.92 |
| P.O. Total : | 11 |  |  | $123,582.96 |
| B0099014 | SEWUP/ JPA | Humanities Complex | Professional Services-Bond | $664,689.00 |
| B0099015 | Keenan & Associates | Humanities Complex | Professional Services-Bond | $25,209.00 |
| B0099016 | Keenan & Associates | Humanities Complex | Professional Services-Bond | $12,110.68 |
| BPO Total : | 3 |  |  | $702,008.68 |
| PO and BPO Total : | 14 |  | TOTAL : | $825,591.64 |