Agenda for the El Camino Community College District Board of Trustees

For

Measure E Bond Fund

Administrative Services

Page No.

A.	Citizens’ Bond Oversight Committee Calendar					1

B.	Category Budgets and Balances							1

C.	Contract – Degenkolb Engineers		 					1

D.	Contract – HGA, Inc.									2

E.	Change Order #1 Primary Electrical Project						2

F.	Purchase Orders and Blanket Purchase Orders					3

Administrative Services

A.	CITIZENS’ BOND OVERSIGHT COMMITTEE MEETING CALENDAR 2006-2007

Meetings will be held in the Boardroom at 3:00 PM on the following dates.

September 27, 2006

November 15, 2006

January 24, 2007

March 14, 2007

May 23, 2007

B.	CATEGORY BUDGETS AND BALANCES

The following table reports Measure E expenditures and commitments through August, 2006.

| CATEGORY | BUDGET | EXPENDED | COMMITTED | BALANCE |
| --- | --- | --- | --- | --- |
| Additional Classrooms and Modernization (ACM) | 175,871,183 | 16,911,921 | 27,830,745 | 131,128,516 |
| Campus Site Improvements (CSI) | 24,467,231 | 1,346,795 | 231,881 | 22,888,555 |
| Energy Efficiency Improvements (EEI) | 3,033,653 | 76,865 | 1,292,445 | 1,664,343 |
| Health and Safety Improvements (HSI) | 134,755,489 | 8,412,899 | 1,925,899 | 124,416,691 |
| Information Technology and Equipment (ITE) | 55,567,921 | 5,100,113 | 173,711 | 50,294,098 |
| Physical Education Facilities Improvements (PEFI) | 1,707,049 | 0.00 | 0.00 | 1,707,049 |
| Refunding Income | 5,980,713 | 0.00 | 0.00 | 5,980,713 |
| TOTAL | 401,383,239 | 31,848,593 | 31,454,681 | 338,079,966 |

### C.	CONTRACT – DEGENKOLB ENGINEERS

It is recommended the Board of Trustees ratify entering into a contract with the structural engineering firm of Degenkolb Engineers to prepare bid specifications and provide construction phase support for the work necessary to repair the fire protection coating of the Fire Building Structure at the Fire Academy.

Dates of Service: September 11, 2006 though March 31, 2007.

Administrative Services

Cost: Not to exceed $15,000 invoiced monthly.

### D.	CONTRACT – HAMMEL, GREEN AND ABRAHAMSON, INC. (HGA)

It is recommended the Board of Trustees ratify entering into a contract with the architectural firm of HGA for the performance of services related to obtaining certification by the Division of the State Architect’s (DSA) for the Science Complex Renovation Project.

HGA is the Architect of Record for this project with DSA, as such project certification documents can only be submitted by HGA.

Dates of Service: February 1, 2006 though December 31, 2006.

Cost: Not to exceed $25,000 invoiced monthly.

E.	CHANGE ORDER #1 PRIMARY ELECTRICAL PROJECT (ECC BID #2005-06/P.O. 89049)

It is recommended the following change order be approved to amend Vector Resources, Inc.’s contract.  Purchase Order #89049

Contractor:	Amount:

Vector Resources, Inc.	$37, 328.71

Total Adjustment to Contract Price:

Original Contract Sum:	$3,282,068.90

Prior Adjustments:	$0.00

Alternate Bid Item Adjustments:	$0.00

Adjustment for this Change:	$37,328.71

Revised Contract Sum:	$3,319,397.61

Reason(s):

|  | - The deletion of the work in the area where the Office Modular Buildings have been installed was necessary to alleviate contract overlap and to minimize contractor conflict. This work was bid and constructed as a part of the modular building installation. | ($28,020.10) |
| --- | --- | --- |
|  | - The removal of eight (8) additional trees was necessary to construct the Southern California Edison (SCE) switchgear yard (near the Parking Lot F structure). | $3,284.70 |
|  | - The installation of additional conduit to feed existing Parking Lot F power needs for future renovation was deemed prudent since the area was being trenched. | $12,514.59 |
| Administrative Services |  |  |
|  | - The installation of a sump pump and lights in the SCE switchgear structure was deemed necessary by the engineer of record for maintenance and to minimize the possibility of water causing an interruption of campus power. | $16,397.56 |
|  | - The removal and installation of three (3) portions of asphalt sidewalk was necessary after tree removal resulted in significant damage to these areas. | $2,151.63 |
|  | - The installation of grounding was deemed necessary for the SCE switchgear equipment and fence. | $29,957.41 |
|  | - The installation of a subterranean drainage system around the SCE switchgear structure was deemed necessary by the engineer. | $1,042.92 |

Adjustment to Contract Time:

Original Contract Time:		370 Days (January 23, 2006-January 31, 2007)

Prior Adjustments:			0 Days

Adjustment for this Change:		10 Days

Revised Completion Date:		February 10, 2007

F.	PURCHASE ORDERS (PO) AND BLANKET PURCHASE ORDERS (BPO)

The following purchase orders have been issued in accordance with the District’s purchasing policy and authorization of the Board of Trustees.  It is recommended that the following purchase orders for Measure “E” expenditures be ratified and that payment be authorized upon delivery and acceptance of the items or services ordered.

|  | P.O. Number | Vendor Name |  | Site Name | Description | P.O. Cost |
| --- | --- | --- | --- | --- | --- | --- |
|  | P0099023 | Christy Construction Inc. |  | Central Plant | Buildings | $1,287.00 |
|  | P0099028 | S & M Moving Systems |  | Central Plant | Contract Services | $9,300.00 |
|  | Total P.O.s : | 2 |  |  |  | $10,587.00 |
|  | B0099022 | Alcal Roofing |  | Humanities Complex | Buildings | $578,028.98 |
|  | B0099024 | John R. Byerly, Inc. |  | Student Services/Activities Center | Architecture & Engineering | $27,000.00 |
|  | B0099025 | Wickwire Gavin Llp |  | Master Planning | Legal -Bond Projects | $48,000.00 |
|  | B0099029 | RMA Group |  | Humanities Complex | Testing & Inspection | $285,000.00 |
| Administrative Services |  |  |  |  |  |  |
|  | B0099031 | C.W. Driver |  | Learning Resource Center | Professional Services-Bond | $550,000.00 |
|  | Total BPOs: | 5 |  |  |  | $1,488,028.98 |
|  | PO and BPO Total: | 7 |  |  | TOTAL : | $1,498,615.98 |