- Agenda for the El Camino Community College District Board of Trustees

- For

- Measure E Bond Fund

- Administrative Services

- Page No.

A.	Category Budgets and Balances							70

B.	Contract – LPA, Inc. – Food Court							70

C.	Bid Award 2006-8 – Fire Academy Room Repairs					71

D.	Change Order - Humanities Building							71

E.	Change Order – Modular Site Infrastructure Project					72

F.	Notice of Job Completion								73

G.	Purchase Orders and Blanket Purchase Orders					73

Board of Trustees Agenda – December 18, 2006                                                   Page 69

- Administrative Services – Measure E Bond Fund

A.	CATEGORY BUDGETS AND BALANCES

The following table reports Measure E expenditures and commitments through November 30, 2006.

| GENERAL OBLIGATION BOND FUND CATEGORIES AND PROJECTS SUMMARY |  |  |  |  |
| --- | --- | --- | --- | --- |
| CATEGORY | BUDGET | EXPENDED | COMMITTED | BALANCE |
| Additional Classrooms and Modernization (ACM) | $175,871,183 | $24,180,848 | $25,634,869 | $126,055,466 |
| Campus Site Improvements (CSI) | 24,467,231 | 1,529,701 | 370,355 | 22,567,175 |
| Energy Efficiency Improvements (EEI) | 3,033,653 | 78,312 | 631,643 | 2,323,698 |
| Health and Safety Improvements (HSI) | 134,755,489 | 9,258,508 | 1,571,226 | 123,925,756 |
| Information Technology and Equipment (ITE) | 55,567,921 | 5,262,829 | 160,654 | 50,144,438 |
| Physical Education Facilities Improvements (PEFI) | 1,707,049 | 0 | 0 | 1,707,049 |
| Refunding Income | 5,980,713 | 0 | 0 | 5,980,713 |
| TOTAL | $401,383,239 | $40,310,197 | $28,368,747 | $332,704,295 |

B.	CONTRACT – LPA, INC. - FOOD COURT

It is recommended the Board of Trustees approve entering into a contract with the architectural firm of LPA, Inc to provide architectural and engineering design services necessary to construct a food service building within the site of the planned Humanities Mall.

The price for these services was negotiated based upon the following factors; scope of work, construction cost and length of performance period.

Dates of Service:  December 19, 2006 through December 31, 2008.

Cost:  Not to exceed $94,500, including reimbursables, invoiced monthly.

Page 70

- Administrative Services – Measure E Bond Fund

C.	BID AWARD 2006-8 – FIRE ACADEMY ROOM REPAIRS

It is recommended that the following contractors be awarded a contract for the respective trades related to the construction of the Fire Academy Room Repairs, in accordance with specifications, terms, and conditions of the above-named bid.  There were no other responses to this request as this is a sole local source.

Vendor	Bid Amount

J. T. Thorpe & Son, Inc.	$35,000

D.	CHANGE ORDER – HUMANITIES BUILDING

It is recommended that the contracts of the prime trade contractors listed below be adjusted by the amounts indicated due to the design changes.

| Total Adjustment to Contract Price: |  |
| --- | --- |
| Original Contract Sum: | $29,364,244 |
| Prior Adjustments: | $16,150 |
| Adjustment for this Change: | $33,025 |
| Revised Contract Sum: | $29,413,419 |

| 1 | SH Fish Electric: Provide credit for the deletion of electrical boxes and duplex electrical outlets for ten classrooms. | ($2,935) |
| --- | --- | --- |
| 2 | Orange Builders: The district requested underground installation of fire sprinkler double check detector valve. | $1,219 |
| 3 | Bennett Landscape: Provide and install 30” x 60” Christy N52 concrete yard box (four stacked on top of each other). Provide pea gravel and back fill to cover fire sprinkler double check detector valve. | $4,207 |
| 4 | Borbon, Inc.: Paint 3/8” eyebrow and steel angle at window opening. Paint continuous 3/8” steel plate at wall opening (all four sides). Paint continuous 3/8” steel plate at the wall openings (all three sides). Paint continuous 3/8” steel angle. Paint continuous 3/8” bent steel plate. Paint all handrails, guardrails, and architectural grills. The “Rebid” of Bid Package 5-1 (Structural Steel) did not include finish painting. | $22,735 |
| 5 | AireMasters Air Conditioning: Relocate the cold-water and hot-water piping to the west of staircase #2 to clear concrete footing. | $6,189 |
| 6 | Superior Wall: Provide a gypsum board wall type “4” chase for the piping in the offices 121A, 221A, 321A. | $1,610 |
| Total Change Proposal(s) |  | $33,025 |

Page 71

- Administrative Services – Measure E Bond Fund

E.	CHANGE ORDER – MODULAR SITE INFRASTRUCTURE PROJECT

This project consists of preparation of site, installation of utilities (electrical, data, water) and the installation of nine classroom modules and five office modules.  This was a fast track project which began on June 9 and was completed in time for the Fall Semester due to the successful cooperation of the college and the contractor.  The following change order reflects changes to the $1,406,243 budget and brings the cost to $1,511,371.  It is recommended the following change order be approved to amend Cornerstone General, Inc.’s contract (Purchase Order 79108).

| Contractor: | Amount |
| --- | --- |
| Cornerstone General, Inc. | $105,128 |
| Total Adjustment to Contract Price: |  |
| Original Contract Sum: | $1,406,243 |
| Prior Adjustments: | $0 |
| Alternate Bid Item Adjustment: | $0 |
| Adjustment for this Change: | $105,128 |
| Revised Contract Sum: | $1,511,371 |

Reason(s):

| - Reduce amount of asphalt paving installed. |  | ($4,349) |
| --- | --- | --- |
| - Delete fire hydrant connection to the domestic water system. |  | ($1,066) |
| - Relocate conduit and wiring to emergency generator. |  | $6,589 |
| - Add additional fire line due to underground obstruction. |  | $4,186 |
| - Increase amount of concrete removed in order to install new duct bank. |  | $1,575 |
| - Provide and install voice/data equipment and cabling to 9 classrooms and 15 offices. |  | $21,066 |
| - Replace deteriorated asphalt paving adjacent to the Community Advancement Building. |  | $4,569 |
| - Install new conduit for emergency generator wiring. |  | $3,696 |
| - Core concrete for 18 - 4” diameter holes into Communications Building. This work was necessary to install voice and data conduit and wiring. |  | $3,053 |
| - Add electrical conduits, pull box, and wiring necessary to install new restroom adjacent to the Community Advancement Building |  | $3,285 |
| - Add electrical & communications conduit to accommodate changed configuration of offices. |  | $19,475 |
| - Accelerate completion of the plumbing and electrical portions of project in order to complete prior to the beginning of the Fall semester. |  | $32,881 |
| - Extra removal & patching for electrical communication due to office movement |  | $2,158 |
| - Replace deteriorated asphalt at Shops access road. |  | $1,552 |
| - Install additional parking stanchion adjacent to new classroom modular buildings. |  | $715 |
| Administrative Services – Measure E Bond Fund |  |  |
| - Install additional asphalt walkway adjacent to new modular classrooms. |  | $2,507 |
| - Relocate catch basins and copper drain lines to accommodate changed configuration of new offices. |  | $3,183 |
| - Replace damaged water valve box in vehicular roadway. |  | $53 |
| Total Change Proposal(s) | $105,128 |  |

F.	NOTICE OF JOB COMPLETION

It is recommended that the Board of Trustees accept as complete the following projects and authorize final payment for the work.  The required work has been completed in accordance with the conditions and specifications of the subject bid and accepted by a District representative.

1.	Project						Contract Amount

Cornerstone General, Inc.				$1,511,371

Modular Site Infrastructure

Bid #: 2005-10

2.	Project						Contract Amount

Modular Structures International, Inc.		$767,697

Modular Buildings

Bid #: 2005-12

G.	PURCHASE ORDERS (PO) AND BLANKET PURCHASE ORDERS (BPO)

The following purchase orders have been issued in accordance with the District’s purchasing policy and authorization of the Board of Trustees.  It is recommended that the following purchase orders for Measure “E” expenditures be ratified and that payment be authorized upon delivery and acceptance of the items or services ordered.

| P.O. Number | Vendor Name | Site Name | Description | P.O. Cost |
| --- | --- | --- | --- | --- |
| P0091228 | Division of the State Architect | Temporary Space/Relocation | Architecture & Engineering | $9,700.00 |
| P0099087 | VWR Scientific | Natural Sciences | New Equipment | $2,407.48 |
| P0099088 | Cal-Ed Optical | Natural Sciences | New Equipment | $4,546.50 |
| P0099090 | Ward's Natural Science | Natural Sciences | New Equipment | $724.69 |
| P0099093 | Boise Cascade | Business | New Equipment | $1,959.79 |
| P0099094 | Dell Computer Corp. | Business | Instructional Computer Equipment | $2,427.17 |
| Administrative Services – Measure E Bond Fund |  |  |  |  |
| P0099095 | CCS Presentation Systems, Inc. | Business | New Equipment | $3,184.41 |
| P0099096 | PC Mall Gov Inc. | Business | Instructional Computer Equipment | $1,139.90 |
| P0099098 | HCD | Temporary Space/Relocation | Buildings | $40.00 |
| P0099100 | Boise Cascade | Business | Instructional Computer Equipment | $830.92 |
| P0099101 | Advanced Masonry & Concrete | Paving Replacement | Site Improvements | $14,810.00 |
| P0099102 | Commercial Fence & Iron Works | Fencing-Replacement | Site Improvements | $2,851.00 |
| P0099104 | Fisher Scientific Education Mater | Natural Sciences | New Equipment | $3,397.14 |
| P0099105 | South Bay Regional Public | Campus Police | New Equipment | $8,157.39 |
| B0099079 | C.W. Driver | Humanities Complex | Professional Services | $3,000.00 |
| B0099097 | Hammel, Green & Abraham | Science Complex Reno | Architecture & Engineering | $25,000.00 |
| B0099103 | Daily Breeze | Master Planning | Advertising-Bond Projects | $5,000.00 |
| B0099106 | Ford Graphics | Learning Resource Center | Blue Printing-Construction | $11,702.99 |
|  | Total POs and BPOs: | 18 | TOTAL: | $100,879.38 |

Page 73