A.	PROJECT BUDGETS

The Facilities Needs Report prepared May 2002, established preliminary budgets for the renovation or replacement of the buildings reported in the categories identified below.  The Needs Report was the basis for determining the amount of bond funding required to complete the facilities upgrade/modernization program.  The preliminary budgets were revised February 17, 2004, when project scopes and timelines were further defined.  Budgets were also revised as of May 16, 2005.  Also included in the needs report was a listing compiled by division of equipment and technology that needed to be replaced or upgraded.

The following table reports expenditures through November 30, 2005.

GENERAL OBLIGATION BOND FUND CATEGORIES AND PROJECTS

(Thru 11/30/05) Datatel 12/1/05

|  | REVISED BUDGET | TOTAL EXPENDITURES | BALANCE |
| --- | --- | --- | --- |
| Additional Classrooms and Modernization (ACM) |  |  |  |
| Acquisitions (0201) | 5,000,000 | 705,867 | 4,294,133 |
| Architectural Barrier Removal Phase 2 (0202) | 1,529,000 | 17,900 | 1,511,100 |
| Athletic Education and Fitness Complex (0203) | 15,718,000 | 267,307 | 15,450,693 |
| Bookstore/Cafeteria Conversion to Admin. (0204) | 6,084,896 | 70,713 | 6,014,183 |
| Business Building Replacement (0205) | 10,926,189 | 135,001 | 10,791,188 |
| Central Plant (0206) | 10,858,000 | 182,894 | 10,675,106 |
| Child Development Center Phase 2 (0207) | 2,525,000 | 29,446 | 2,495,554 |
| Crenshaw Blvd. Frontage Enhancement (0208) | 1,100,000 | 12,927 | 1,087,073 |
| Fire Academy Structure (0209) | 791,375 | 9,349 | 782,026 |
| Fire Program Facility (0210) | 123,000 | 1,601 | 121,399 |
| Humanities Complex Replacement (0212) | 23,120,064 | 1,409,764 | 21,710,300 |
| Learning Resource Center Addition (0213) | 7,100,000 | 118,655 | 6,981,345 |
| Manhattan Bch Blvd. Parking Structure & Entrance (0214) | 216,232 | 716 | 215,516 |
| Remodeling Phase Two (0216) | 157,625 | 34,540 | 123,085 |
|  | REVISED BUDGET | TOTAL EXPENDITURES | BALANCE |
| Remodeling Phase Three (0217) Science Complex Renovation (0219) | 8,715,875 6,721,738 | 101,212 6,448,942 | 8,614,663 272,796 |
| Signage and Wayfinding (0224) | 2,600,000 | 52,745 | 2,547,255 |
| Student Services and Activities Replacement (0220) | 31,928,118 | 390,819 | 31,537,299 |
| Temporary Space and Relocation Costs (0221) | 2,000,000 | 637,139 | 1,362,861 |
| Master Planning (0223) |  | 285,039 | (285,039) |
| Reserve for Contingencies (0299) | 37,748,071 | - | 37,748,071 |
| Total Additional Classrooms and Modernization | 174,963,183 | 11,161,708 | 163,801,475 |
| Campus Site Improvements: Accessibility, Safety / Security (CSI) |  |  |  |
| Asphalt Resurfacing - All Lots (0301) | 400,000 | 14,796 | 385,204 |
| Emergency Generators and Distribution (0302) | 2,265,000 | 16,660 | 2,248,340 |
| Emergency Power to Security Lighting (0303) | 175,000 | 1,287 | 173,713 |
| Entrance - Redondo Beach Blvd. to Lot H (0304) | 400,000 | 4,322 | 395,678 |
| Fencing Replacement and Additions (0305) | 375,000 | 2,758 | 372,242 |
| Landscaping & Irrigation System Replacements (0306) | 2,540,000 | 41,269 | 2,498,731 |
| Lighting - Upgrade / Replace All Lots (0308) | 2,440,000 | 17,947 | 2,422,053 |
| Lot F Parking Structure Improvements (0309) | 1,632,000 | 17,155 | 1,614,845 |
| Lot H Parking Structure (0310) | 8,348,666 | 705,075 | 7,643,591 |
| Paving Replacement - All Walks and Driveways (0311) | 2,187,000 | 16,086 | 2,170,914 |
| Pedestrian Walks at Manhattan Bch Blvd & Lot E (0312) | 81,600 | 600 | 81,000 |
| Security Video (0313) | 180,000 | 7,751 | 172,249 |
| Voice / Data / Signal Site Duct Bank (0314) | 1,945,181 | 83,760 | 1,861,421 |
| Reserve for Contingencies (0399) | REVISED BUDGET 1,757,784 | TOTAL EXPENDITURES - | BALANCE 1,757,784 |
| Total Campus Site Improvements: Accessibility, Safety / Security | 24,727,231 | 929,467 | 23,797,764 |
| Energy Efficiency Improvements (EEI) |  |  |  |
| Energy Efficiency Improvements Phase Two (0402) | 2,818,000 | 43,000 | 2,775,000 |
| Reserve for Contingencies (0499) | 215,653 | - | 215,653 |
| Total Energy Efficiency Improvements | 3,033,653 | 43,000 | 2,990,653 |
| Health and Safety Improvements (HSI) |  |  |  |
| Administration (0501) | 4,367,732 | 70,375 | 4,297,357 |
| Art & Behavioral Sciences (0502) | 12,247,136 | 199,377 | 12,047,759 |
| Auxiliary Warehouse (0504) | 105,042 | 1,259 | 103,783 |
| Communications (0507) | 8,223,354 | 216,445 | 8,006,909 |
| Construction Technology (0508) | 943,970 | 16,167 | 927,803 |
| Domestic Water System (0509) | 2,488,800 | 67,511 | 2,421,289 |
| Facilities and Receiving (0510) | 1,985,416 | 134,589 | 1,850,827 |
| Fire Alarm (0511) | 780,800 | 8,707 | 772,093 |
| Firelines (0512) | 1,837,503 | 80,977 | 1,756,526 |
| Hazardous Materials Abatement (0513) | 200,000 | 65,893 | 134,107 |
| Library (0515) | 7,876,509 | 416,247 | 7,460,262 |
| Marsee Auditorium (0516) | 6,670,843 | 109,828 | 6,561,015 |
| Math & Computer Sciences (0517) | 10,761,643 | 176,745 | 10,584,898 |
| Music (0518) | 8,896,846 | 223,372 | 8,673,474 |
| Natural Gas System (0519) | 488,000 | 5,480 | 482,250 |
| North Gymnasium (0520) | REVISED BUDGET 3,248,993 | TOTAL EXPENDITURES 255,827 | BALANCE 2,993,166 |
| Physical Education and Men's Shower (0521) | 4,216,871 | 65,736 | 4,151,135 |
| Planetarium (0522) | 559,465 | 12,671 | 546,794 |
| Pool and Health Center (0523) | 8,273,592 | 136,497 | 8,137,095 |
| Primary Electrical Distribution System (0524) | 13,460,000 | 457,890 | 13,002,110 |
| Reimbursements (0525) | 1,456,353 | 1,456,353 | - |
| Security Systems (0526) | 1,313,664 | 29,659 | 1,284,005 |
| Sewer System (0527) | 1,964,200 | 21,752 | 1,942,448 |
| Social Sciences (0528) | 7,415,520 | 148,852 | 7,266,668 |
| Storm Drain System (0530) | 1,083,909 | 12,049 | 1,071,860 |
| Technical Arts (0531) | 5,600,000 | 105,624 | 5,494,376 |
| Shops (0533) | 10,600,000 | 208,607 | 10,391,393 |
| Reserve for Contingencies (0599) | 8,337,328 | - | 8,337,328 |
| Total Health and Safety Improvements | 135,403,489 | 4,704,490 | 130,698,999 |
| Information Technology and Equipment (ITE) |  |  |  |
| Behavioral and Social Sciences (0601) | 579,077 | 22,984 | 556,093 |
| Business (0602) | 1,123,650 | 438,401 | 685,249 |
| Facilities Planning and Services (0603) | 1,818,724 | 283,304 | 1,535,420 |
| Fine Arts (0604) | 2,805,096 | 328,212 | 2,476,884 |
| Health Sciences and Athletics (0605) | 1,203,993 | 177,688 | 1,026,305 |
| Humanities (0606) | 607,033 | 150,534 | 456,499 |
| Industry and Technology (0607) | REVISED BUDGET 1,771,641 | TOTAL EXPENDITURES 422,712 | BALANCE 1,348,929 |
| Information Technology (0608) | 14,557,510 | 1,784,540 | 12,772,970 |
| Learning Resources (0609) | 4,665,775 | 137,253 | 4,528,522 |
| Math (0610) | 688,661 | 134,997 | 553,664 |
| Natural Sciences (0611) | 3,002,285 | 585,119 | 2,417,166 |
| Nursing (0612) | 252,651 | 116,478 | 136,173 |
| Student and Community Advancement (0613) | 567,500 | 169,879 | 397,621 |
| Interfund Transfer (0614) | 141,150 | 141,150 | - |
| Phase II, III, IV Purchases (0697) | 12,686,900 | - | 12,686,900 |
| Installation Contingency (0698) | 4,464,194 | - | 4,464,194 |
| Reserve for Contingencies (0699) | 3,746,018 | - | 3,746,018 |
| Total Information Technology and Equipment | 54,681,858 | 4,893,250 | 49,788,608 |
| Physical Education Facilities Improvements (PEFI) |  |  |  |
| Baseball Field (0701) | 1,091,800 | - | 1,091,800 |
| North Field (0702) | 481,600 | - | 481,600 |
| Sand Volleyball (0703) | 12,300 | - | 12,300 |
| Reserve for Contingencies (0799) | 121,349 | - | 121,349 |
| Total Physical Education Facilities | 1,707,049 | - | 1,707,049 |
| Refunding Income | 6,866,776 $ 401,383,219 | 0 $ 21,731,914 | 6,866,766 $ 379,651,305 |

B.	CITIZENS’ BOND OVERSIGHT COMMITTEE

The next meeting of the Citizens’ Bond Oversight Committee is scheduled for January 25 at 9 a.m.

# C.	CONTRACT -  TMAD TAYLOR GAINES

It is recommended that the Board of Trustees approve entering into a contract with TMAD Taylor Gaines for various and ongoing engineering services from December 22, 2005 through December 31, 2007.  The related information is provided:

Item 1 – Civil Engineering Services for the installation of additional modular buildings: $45,180.  Account number 42 - 221

Item 2 – Civil Engineering Services for Student Services and Activities Center Replacement Project: $49,010.  Account number 42 - 220

Item 3 – Perform various engineering services as needed, including utility line routing and elevations, surveying and site civil engineering - $50,000

Item 4 – Reimbursable expenses: $5,000.  Account number 42-223

Total costs of contract:  $149,190.00

# CONTRACT – FLEWELLING AND MOODY

It is recommended that the Board of Trustees approve entering into a contract with Flewelling and Moody to provide architectural and engineering design services for the renovation of the Bookstore/Cafeteria.  The negotiated price for these services was determined by local agency guidelines, which include building type, construction budget, and new construction vs. renovation.  Dates of Service:  January 1, 2006 through December 31, 2008.  Cost:  Not to exceed $587,000, including reimbursables, invoiced monthly.  Account Number:  Fund 42 Location 0204.

E.	BID  2005-08/ELEVATOR MODERNIZATION

It is recommended that Bid 2005-08 be awarded to the following vendor for Elevator Modernization project for the Art and Behavioral Sciences Building in accordance with the specifications, terms, and conditions of the above named bid.

P.O.	              Vendor			Bid Amount

TBD	                  University Elevator [1]         $85,000 including materials, delivery, and

any applicable taxes.

Other Bidders: None

“No Bid” Responses:  None

Non-Responses:  None

F.	PURCHASE ORDERS

The following purchase orders have been issued in accordance with the District’s purchasing policy and authorization of the Board of Trustees.  It is recommended that the following purchase orders for Measure “E” expenditures be ratified and that payment be authorized upon delivery and acceptance of the items or services ordered.

P.O.

Number	Vendor Name	Site Name	Description	  P.O. Cost

P0089040	Division of the State Architect	Firelines	Architecture & Engineering	$2,070.02

P0089041	Division of the State Architect	Firelines	Architecture & Engineering	$2,700.00

Total : 	2	$4,770.02

B0089035	Doja, Inc.	Humanities Complex 	Site Improvements	$285,000.00

B0089036	Louis Todd Corporati	Humanities Complex 	Site Improvements	$358,000.00

B0089037	HPS Mechanical, Inc.	Humanities Complex 	Site Improvements	$544,910.00

B0089038	Keenan & Associates	Humanities Complex 	Professional Services-Bon	$89,100.00

Total : 	4	$1,277,010.00

Total POs and BPOs : 	6	TOTAL :	$1,281,780.02